## Website Plan
Tasks | Resources | Time in days
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
PLANNING & LEARNING
Plan a website idea | Anna | bar: Time in days 1 to Time in days 2
Produce Wire and Navigation Diagrams | Anna | bar: Time in days 3
Plan colour and style theme | Anna | bar: Time in days 4
Learn HTML | Anna | bar: Time in days 5 to Time in days 9
Learn CSS | Anna | bar: Time in days 10 to Time in days 14
CREATING TEMPLATES (PLACEMENTS ONLY)
Produce HTML templates of diagrams | Anna | bar: Time in days 15 to Time in days 17
Produce Navigation Bar | Anna | bar: Time in days 18
Produce Header | Anna | bar: Time in days 19
Produce Footer | Anna | bar: Time in days 20
CREATING (GRAPHICS)
Create buttons for navigation | Anna | bar: Time in days 21
Create/collate images/videos for website | Anna | bar: Time in days 22 to Time in days 24
Check file format of images is fit for purpose | Anna | bar: Time in days 25
Edit and save images accordingly in GIMP | Anna | bar: Time in days 26 to Time in days 27
CREATING (WEBSITE)
Add graphics/videos | Anna | bar: Time in days 28 to Time in days 30
Add text | Anna | bar: Time in days 31 to Time in days 33
Organise file storage and directory | Anna | bar: Time in days 34
Create anchor to links | Anna | bar: Time in days 35
Create CSS based on theme | Anna | bar: Time in days 36 to Time in days 37
Final touches to website | bar: Time in days 38 to Time in days 39
VERIFICATION
Check text for authenticity | Anna | bar: Time in days 40
Validate HTML website for errors | Anna | bar: Time in days 41
Validate CSS for errors | Anna | bar: Time in days 42
Final editing to rectify errors | Anna | bar: Time in days 43 to Time in days 46
TESTING
Create test plan for website | Anna | bar: Time in days 47
Test links | Anna | bar: Time in days 48
Test navigation | Anna | bar: Time in days 49
Test browser compatibility | Anna | bar: Time in days 50 to Time in days 52
SIGN OFF
Make final changes to the website | Anna | bar: Time in days 53 to Time in days 55
DEPLOYMENT | Anna
Upload website to Filezilla | Anna | bar: Time in days 56 to Time in days 57
LIVE TESTING
Test links | Anna | bar: Time in days 58
Test navigation | Anna | bar: Time in days 59
Test overall website | Anna | bar: Time in days 60 to Time in days 62